## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Creating the Git Repository | Must Have | GitHub | Debrupa Mukherjee | Completed
S2 | S2 | US-001 | Model Research | Must Have | Research from AI tools and existing documents | Debrupa Mukherjee | Completed
S3 | S3 | US-001 | Python Task for Practice | Must Have | Google Colab | Debrupa Mukherjee | Completed
S4 | S4 | US-001 | SQL Task for Practice | Must Have | Google Colab | Debrupa Mukherjee | Completed
S5 | S5 | US-001 | Planning- defining the project, deciding upon the scope of the project | Must Have | Research from AI tools | Group | Completed
S7 | S7 | US-001 | Tech Stack and Data Source Selection | Must Have | Research from AI tools | Group | Completed
S8 | S8 | US-001 | System architecture design | Must Have | Research from AI tools | Group | Completed
S9 | S9 | US-001 | Database Schema Design(soc_db collections setup) | Must Have | Research from AI tools | Debrupa & Sakshee | Completed
S10 | S10 | US-001 | Engine 1-3 Development: Live Feed Ingestion (Malware, Phishing, DDoS) | Must Have | MongoDB Atlas & APIs | Debrupa & Sakshee | Completed
S11 | S11 | US-001 | Engine 4 & 5 Development: Enrichment (MITRE Tagging & GeoIP) | Must Have | GeoLite2 DB & MITRE Mapping | Debrupa & Sakshee | Completed
S12 | S12 | US-001 | System Integration: Concurrent Engine Testing & Data Validation | Must Have | All Ingestion Engines | Debrupa & Sakshee | Completed
S13 | S13 | US-001 | Data Pre-processing & Column Standardization | Must Have | Pandas, Dataset from S10 | Sai Narendra & Navya | Completed
S14 | S14 | US-001 | Analytical Aggregation & Grouping | Must Have | Clean Data | Sai Narendra & Navya | Completed
S15 | S15 | US-001 | Interactive Visualization Development | Must Have | Aggregated Data | Sai Narendra & Navya | Completed
S16 | S16 | US-001 | Geospatial Intelligence: Country-wise attack density mapping (Choropleth) | Must Have | Plotly, Cleaned country column | Akhila, Jidnyasa | Completed
S17 | S17 | US-001 | Hierarchical Structural Logic: Treemap development for System-to-Attack mapping | Must Have | Pandas Aggregation, Target_System | Akhila, Jidnyasa | Completed
S18 | S18 | US-001 | Advanced Interaction: Sunburst Chart integration for parent-child threat drill-down | Must Have | S17 logic, Standardized attack_type | Akhila, Jidnyasa | Completed
S19 | S19 | US-001 |  | Must Have |  |  | Completed
S20 | S20 | US-001 |  | Must Have |  |  | Completed
S21 | S21 | US-001 |  | Must Have |  |  | Completed
S22 | S22 | US-001 |  | Must Have |  |  | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlogs
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Creating the Git Repository |  |  | Debrupa Mukherjee | Others | Completed
US-001 | 2 | Model Research |  |  | Debrupa Mukherjee | Research | Completed
US-001 | 3 | Python Task for Practice |  |  | Debrupa Mukherjee | Prompt Engg | Completed
US-001 | 4 | SQL Task for Practice |  |  | Debrupa Mukherjee | Prompt Engg | Completed
US-001 | 5 | Planning- defining the project, deciding upon the scope of the project |  |  | Group | Others | Completed
US-001 | 6 | Tech Stack and Data Source Selection |  |  | Group | Others | Completed
US-001 | 7 | System architecture design |  |  | Group | Others | Completed
US-001 | 8 | Database Schema Design(soc_db collections setup) |  |  | Debrupa & Sakshee | Others | Completed
US-001 | 9 | Engine 1-3 Development: Live Feed Ingestion (Malware, Phishing, DDoS) |  |  | Debrupa & Sakshee | Coding | Completed
US-001 | 10 | Engine 4 & 5 Development: Enrichment (MITRE Tagging & GeoIP) |  |  | Debrupa & Sakshee | Coding | Completed
US-001 | 11 | System Integration: Concurrent Engine Testing & Data Validation |  |  | Debrupa & Sakshee | Coding | Completed
US-001 | 12 | Data Pre-processing & Column Standardization |  |  | Sai Narendra & Navya | Coding | Completed
US-001 | 13 | Analytical Aggregation & Grouping |  |  | Sai Narendra & Navya | Coding | Completed
US-001 | 14 | Interactive Visualization Development |  |  | Sai Narendra & Navya | Dashboarding | Completed
US-001 | 15 | Geospatial Intelligence: Country-wise attack density mapping (Choropleth) |  |  | Akhila, Jidnyasa | Coding | Completed
US-001 | 16 | Hierarchical Structural Logic: Treemap development for System-to-Attack mapping |  |  | Akhila, Jidnyasa | Coding | Completed
US-001 | 17 | Advanced Interaction: Sunburst Chart integration for parent-child threat drill-down |  |  | Akhila, Jidnyasa | Coding | Completed
US-001 | 18 | [5 empty] | Completed
US-001 | 19 | [5 empty] | Completed
US-001 | 20 | [5 empty] | Completed
US-001 | 21 | [5 empty] | Completed
Note on D1: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E1: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I2: This is the total task estimated in hours for all the user stories
Note on J2: Pending effort hours after completion of day 1 work
Note on K2: Pending effort hours after completion of day 2 work
Note on L2: Pending effort hours after completion of day 3 work
Note on M2: Pending effort hours after completion of day 4 work
Note on N2: Pending effort hours after completion of day 5 work
Note on O2: Pending effort hours after completion of day 6 work
Note on P2: Pending effort hours after completion of day 7 work
Note on Q2: Pending effort hours after completion of day 8 work
Note on R2: Pending effort hours after completion of day 9 work
Note on S2: Pending effort hours after completion of day 10 work
Note on T2: Pending effort hours after completion of day 11 work
Note on U2: Pending effort hours after completion of day 12 work
Note on V2: Pending effort hours after completion of day 13 work
Note on W2: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Week | Impediments | Action Taken
Sprint 1 | 1 | Lack of clear knowledge on the Python ans SQL task | Discussion with mentor and peers to get clarity
Sprint 2 | 2 | Lack of clarity regarding the project demo that was given | Discussion with mentor to get clarity
Sprint 2 | 2 | Doubt about sources of capturing live data from network | Discussion with mentor and peers to get clarity
Sprint 2 | 2 | Confusion regarding the created architecture would be fine | Discussion with mentor to get clarity
Sprint 3 | 4 | Confusion regarding capturing live data and storing it in cloud for analysis | Discussion with mentor to get clarity
Sprint 4 | 6 | Agile template confusion | Discussion with mentor to get clarity

## Retrospection
Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
Sprint 1 | 2026-01-08 | 2026-01-16 | Sakshee & Debrupa | Automated engine health checks | Manual data validation | Concurrent engine processing | Established stable live ingestion layer
Sprint 2 | 2026-01-19 | 2026-01-23 | Sai Narendra & Navya | Automated data cleaning scripts | Manual column renaming | Using Pandas for aggregation | Standardized dataset for dashboarding
Sprint 3 | 2026-01-27 | 2026-01-30 | Akhila, Jidnyasa | Advanced hierarchical charting | Static geographic lists | Using Plotly for interactivity | Generated interactive geospatial and Sunburst maps
Sprint 4 | 2026-02-02 | 2026-02-15 | Stuti & Chetna | Dash callbacks | Static layouts | Bootstrap styling | Finalized responsive UI